## Sheet1
Project Name: | Virtual Library Management System
Project Start: | 2024-05-13
Current Date: | 2024-06-29
Weeks in Progress: | 7
[6 empty] | 2024-05-13 | 2024-05-20 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-17 | 2024-06-24 | 2024-06-29
Task | Project Lead | Start Date | End Date | Days | Progress | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Planning Stage
Task: class headers and .h/.cpp files | Taylor Montgomery | 2024-05-13 | 2024-05-20 | 7 | 100%
Task: GitHub | Riley Pence | 2024-05-13 | 2024-06-30 | 48 | 50%
Task: Administration | William Denson | 2024-05-13 | 2024-06-30 | 48 | 55%
Task: UX | John Parker | 2024-05-13 | 2024-06-30 | 48
Task: Algorithm/Pseudocode design | Cesar Ortiz | 2024-05-13 | 2024-06-30 | 48 | 50%
Task: System Analysis | Constantine Ewan | 2024-05-13 | 2024-06-30 | 48 | 50%
Prototyping Stage (Agile Methods)
Task: Plan | Taylor Montgomery | 2024-05-13 | 2024-06-30 | 48
Task: Develop | Riley Pence | 2024-06-04 | 2024-06-30 | 26
Task: Deploy | William Denson | 2024-06-05 | 2024-06-30 | 25
Task: Test | John Parker | 2024-06-06 | 2024-06-30 | 24
Task: Design | Cesar Ortiz | 2024-06-07 | 2024-06-30 | 23
Task: Review | Constantine Ewan | 2024-06-08 | 2024-06-30 | 22
Coding Responsibilities
Task: Binary Search Tree | Taylor Montgomery | 2024-05-23 | 2024-06-07 | 15
Task: Password Methods / User Backend Dataset | Riley Pence | 2024-06-03 | 2024-06-14 | 11
Task: Book Data Sets | William Denson | 2024-06-03 | 2024-06-14 | 11
Task: Book Management Queue | John Parker | 2024-06-03 | 2024-06-14 | 11
Task: Login Server/Welcome Page | Cesar Ortiz | 2024-05-27 | 2024-06-07 | 11
Task: Quality Control Testing | Constantine Ewan | 2024-06-03 | 2024-06-16 | 13
Debugging Stage (For Future Use)
Task: | Taylor Montgomery | 2024-06-17 | 2024-07-06 | 19
Task: | Riley Pence | 2024-06-17 | 2024-07-06 | 19
Task: | William Denson | 2024-06-17 | 2024-07-06 | 19
Task: | John Parker | 2024-06-17 | 2024-07-06 | 19
Task: | Cesar Ortiz | 2024-06-17 | 2024-07-06 | 19
Task: | Constantine Ewan | 2024-06-17 | 2024-07-06 | 19
New Features (TBD)
Task: | Taylor Montgomery | 2024-06-17 | 2024-07-06 | 19
Task: | Riley Pence | 2024-06-17 | 2024-07-06 | 19
Task: | William Denson | 2024-06-17 | 2024-07-06 | 19
Task: | John Parker | 2024-06-17 | 2024-07-06 | 19
Task: | Cesar Ortiz | 2024-06-17 | 2024-07-06 | 19
Task: | Constantine Ewan | 2024-06-17 | 2024-07-06 | 19